## Stakeholder Register Template
Stakeholder Register
Project Name | Cross Country Tour 2023 |  |  | Project Manager | Sekinat Shittu |  | Project Phase |  | Initiation |  | Date | 2023-04-07
Sr. No. | Name | Designation | Department | Role | Contact | Category | Interest | Influence | Expectations | Comms requirements | Comms frequency | Comments
1 | Frank Agoh | Managing Director | Management | Project Sponsor | Phone: +61 4834467651 Email:Frank.agoh@gmail.com | Internal |  |  | To deliver an aplication on time that meets the requirement of the Users and the business | Video Conference and Email | Weekly
2 | Accountant | Finance officer | Finance | user | Phone: +65 0546533151 Email: service.R-user@gmail.com | Internal |  |  | To manage cash flow, balance company accounts and reduce cash handling | Email and Telephone | Weekly
3 | Returning Customer | User | External | User | Phone: +65 8542533152 Email: service.R-user@gmail.com | External |  |  | To have an online booking system, online check in option, flexible payment option and advance booking | Email
4 | New Customer | User | External | User | Phone: +65 8542533153 Email: service.N-user@gmail.com | External |  |  | To have an system that will enable customers book and check in online | Email
5 | Admin | Staff | Internal | User | Phone: +65 9652534412 Email: service.N-user@gmail.com | Internal |  |  | An application that is customer friendly, effiecient and helps the ease running of the company | Email and Telephone | Bi-weekly
6 | Customer Service Representative | Staff | Internal | User | Phone: +65 9652534412 Email: Customer-service@gmail.com | Internal |  |  | To have an application that is user friendly for both customer and staff | Email | Bi-weekly
7 | Olawale Johnson | Project manager | External | Project Manager | Phone: +44 5871512134 Email: wale.johnson@gmail.com | External |  |  | Quality project to be delivered on time and within budget. | Video Conference, Email and Telephone | Daily
8 | Precious Njobuenwu | Business Analyst | External | Business Analyst | Phone: +91 9852425634 Email: precious.njo@gmail.com | External |  |  | Complete requirement elicitation and sign off for the development team. | Video Conference, Email and Telephone | Daily
9 | Ikechukwu Nwegbu | Designer | External | Technology | Phone: +91 9852425634 Email: ikwechukwu.n@gmail.com | External |  |  | Create design that meets the project goals and user needs. | Video Conference, Email and Telephone | Daily
10 | Naheem Taiwo | Software Devoloper | External | Technology | Phone: +61 4854665621 Email: Naheem.taiwo@gmail.com | External |  |  | Develop a responsive system based on requirements | Video Conference, Email and Telephone | Daily
9 | Shedlis Gana | Software Tester | External | Technology | Phone: +61 48546645730 Email: Shedlis.gana@gmail.com | External |  |  | To ensure the system is bug free. | Video Conference, Email and Telephone | Daily
Medium
Low
High